## ProductBackLog
Project Name:NeuroMatter: Universal Local AI Hub Group Members:Duru Deniz Alptekin, Şevval Acar, Kaan Efe Koygun, Ege Haktan Aykut, Ali Utku Aydın, Eren Karlı, Deren Kocabaş, Efe Berkay Soyucak.
# | Product BackLog
1 | Database Planning
2 | SQLCipher Encrypted Database Setup
3 | Flutter Cross-Platform UI Framework
4 | Local Authentication & Role Access
5 | CSA Matter SDK Environment Config
6 | Environmental Sensor Monitoring Service
7 | YOLOv8n Local Inference Testing
8 | Caregiver Threshold Management UI
9 | Local Notification & Alert Service
10 | Matter Device Provisioning Workflow
11 | Performance Testing
12 | Grafana Real-Time Data Visualization

## Sprint-1
SPRINT-1
STAFF | ACTION | STATUS | PRIORITY | START | FINISH | DURATION (DAYS) | NOTES AND COMMENTS
Developer, Product Owner | General Planning | In Progress | High | 2026-03-23 | 2026-03-25 | 3 | Design and document the core database schema for sensors, users, and logs.
Developer | Flutter Single-Codebase UI Core | Ready to Start | High | 2026-03-26 | 2026-04-01 | 7 | Integrate 256-bit AES encryption to protect local databases against unauthorized access.
Developer | Local Auth & Resident Profile Setup | Ready to Start | Medium | 2026-04-02 | 2026-04-05 | 4 | Initialize the cross-platform UI framework to ensure consistent performance on Android and iOS.
BACKLOG
As a caregiver, I want to log in safely so that nobody else can see the patient's private information.
STATUS: Ready to Start
As a manager, I want to invite other helpers to the app so that they can also look after the patient.
STATUS: Ready to Start
Developer
Developer

## Sprint-2
SPRINT-2
STAFF | ACTION | STATUS | PRIORITY | START | FINISH | DURATION (DAYS) | NOTES AND COMMENTS
Developer | CSA Matter SDK & Local Pairing | Not Started | High | 2026-04-06 | 2026-04-13 | 8 | Monitoring light, sound, and vibrations.
Developer | Environmental Sensor Monitoring | Not Started | High | 2026-04-14 | 2026-04-18 | 5 | Monitoring light, sound, and vibrations.
Developer | Database Planning | Not Started | High | 2026-04-19 | 2026-04-20 | 2 | Configure the Matter SDK environment to enable local communication with smart home devices.
BACKLOG
As a caregiver, I want to see if the room is too loud or too bright so that I can keep the patient comfortable.
STATUS: Not Started
Developer
As a caregiver, I want to turn off lights or music using the app so that I don't disturb the patient.
STATUS: Not Started
Developer

## Sprint-3
SPRINT-3
STAFF | ACTION | STATUS | PRIORITY | START | FINISH | DURATION (DAYS) | NOTES AND COMMENTS
Developer | YOLOv8n & Qwen2-VL-2B Local Inference | Not Started | High | 2026-04-21 | 2026-05-03 | 9 | Deploying AI models via TFLite.
Developer | FastAPI & C++ Asynchronous Bridge | Not Started | High | 2026-05-04 | 2026-05-11 | 6 | Connecting AI logic to hardware control.
Developer | Caregiver Threshold Configuration | Not Started | Medium | 2026-05-12 | 2026-05-18 | 5 | UI for personalized sensory limits.
BACKLOG
As a family member, I want to get a quick message on my phone if the patient falls so that I can check on them right away.
STATUS: Not Started
As a caregiver, I want to see a list of past warnings so that I can know how the patient's day went
STATUS: Not Started
Developer
Developer
As a caregiver, I want to set a limit for noise and light so that the app warns me when it gets uncomfortable for the patient.
STATUS: Not Started
Developer

## Sprint-4
SPRINT-4
STAFF | ACTION | STATUS | PRIORITY | START | FINISH | DURATION (DAYS) | NOTES AND COMMENTS
Developer | Grafana Edge-Based Visualization | Not Started | High | 2026-05-19 | 2026-05-26 | 6 | Validating system response speed.
Developer | SQLCipher 256-bit AES DB Integration | Not Started | Low | 2026-05-27 | 2026-05-29 | 3 | Monitoring dashboard.
Developer | Performance Testing | Not Started | Low | 2026-05-30 | 2026-06-02 | 4 | Monitoring dashboard.
BACKLOG
As a family member, I want the camera and room information to stay private inside the house so that it never goes online.
STATUS: Not Started
As a family member, I want the app to keep ringing my phone until I answer if there is a big emergency in the room so that I don't miss it.
STATUS: Not Started
Developer
Developer

## KeyDropdowns
KEY DROPDOWNS - DO NOT DELETE
PRIORITY KEY | STATUS KEY
High | In Progress
Medium | Ready to Start
Low | Complete
On Hold
Testing
Not Started

## Templates
TEMPLATES
ASSIGNED TO | KANBAN CARDS
XX
XX
XX
XX
XX
XX
XX
XX
XX
XX
XX
XX
XX
XX
XX
XX
XX
XX
XX
XX
As a [role], I want [goal], so that [benefit]
STATUS: Note Status Here
As a [role], I want [goal], so that [benefit]
STATUS: Note Status Here
As a [role], I want [goal], so that [benefit]
STATUS: Note Status Here
As a [role], I want [goal], so that [benefit]
STATUS: Note Status Here
As a [role], I want [goal], so that [benefit]
STATUS: Note Status Here
As a [role], I want [goal], so that [benefit]
STATUS: Note Status Here